Business Requirements Document

DRS Marketing Agent (DMA)

The Claude-powered marketing operating system for launching and scaling

Deposit Return Systems in any geography

Engine: DMS (DRS Marketing System)  ·  Part of RMOS / Project MARS

Version 1.0  ·  Owner: Director Marketing  ·  Status: Build-ready

# Contents

# 0. What this document is

This document is the complete, build-ready specification of the DRS Marketing Agent (DMA) — a Claude-powered system that runs the marketing lifecycle of launching and scaling a Deposit Return System (DRS) in any geography.

It is written so that it can be used in two ways:

- To build the agent — upload this document to Claude and it contains everything required to construct the DMA: the architecture, every stage, every workflow, every input and output, every approval gate, and every conditional (if/but) branch.

- To explain the initiative — it can be read or presented to leadership to show exactly what we are building, how it works, where humans stay in control, and how each launch makes the next one faster.

Build contract: statements marked MUST are mandatory, SHOULD are strongly recommended, MAY are optional. Conditional logic is written as IF … THEN … ELSE …

Relationship to the DMS: this document is a superset of the Director’s DRS Marketing System (DMS). It carries the DMS in full — the North Star, the five operating layers, all nine workflows, the RACI, the governance cadence, the KPI tree, the decision points, the feedback loops, the geography instantiation, the minimum-viable definition, and the system-health indicators — and wraps the agent mechanics (orchestrator, auditor, memory, gates) around it.

# 1. System foundations

## 1.1 Purpose & design philosophy

DMS is the reusable marketing operating architecture for launching and scaling Deposit Return Systems across geographies. Its purpose is to help Recykal enter any DRS geography with a repeatable public-acceptance, stakeholder-alignment, launch-readiness, and collection-adoption system.

Core belief: DRS is not primarily a waste-management project. DRS is a behaviour-change program. Public acceptance determines collection performance.

## 1.2 North Star — DRS Adoption Index

DRS Adoption Index = (Public Awareness × Stakeholder Alignment × Return Participation) ÷ (Trust & Friction Barriers)

The system improves when more people understand DRS, more stakeholders support it, more containers are returned, and trust/friction barriers decline. Every stage MUST roll its KPIs up to one of these four terms.

## 1.3 The five DMS operating layers

The marketing engine operates in five layers; the agent’s stages sit inside them.

| Layer | Purpose | Core modules | Primary owner |
| --- | --- | --- | --- |
| 1 · Evidence | Establish why DRS matters here | Impact research, waste leakage & litter, tourism/public-space impact, international benchmarks, economic & environmental cases, local behaviour insights | Marketing |
| 2 · Coalition | Align stakeholders before public launch | Stakeholder mapping, champion identification, government/regulator alignment, retailer/brand/NGO/school/media/academic engagement | Government Affairs, Marketing, Partnerships |
| 3 · Narrative | Give every stakeholder a reason to support & repeat | Core story, persona messages, FAQ kits, whitepapers, op-eds, roundtables, demonstration content | Marketing & Communications |
| 4 · Public Adoption | Drive awareness, participation & repeat returns | School/retail/airport/transit awareness, social & influencer activation, launch events, machine demos, return nudges | Marketing, Retail/Partner, Operations |
| 5 · Trust & Optimization | Protect reputation, reduce friction, improve collection | Media monitoring, rapid response, testimonials, milestone comms, return-rate / cost-per-container / active-user / retail-participation tracking | Communications, Operations, Marketing |

## 1.4 The DRS Narrative Adoption Flywheel

Research → Stakeholder Mapping → Narrative Development → Stakeholder Alignment → Consumer Awareness → Launch Readiness → Reputation Management → Collection Optimization → Narrative Amplification → (back to) Research.

It is a flywheel, not a straight line: each completed cycle strengthens the next, and proof from one geography becomes the starting evidence for the next.

## 1.5 Scope

In scope — the agent runs these: Stages 1–10 and 13–16 (configuration, geography, market, stakeholder, resistance, DRS marketing system, GTM, acquisition, consumer engagement, communication & BTL, analytics, metrics, knowledge, AI copilot) plus the governance & cadence layer.

Tracked dependencies — the agent coordinates but does NOT run these: Stage 11 (Infrastructure) and Stage 12 (Operations). The agent ingests their readiness and performance data, gates against them, and raises risks; physical execution is owned by humans/operations.

Out of scope: actual publishing/field execution, government approvals and signatures, and physical machine deployment & logistics. The agent prepares, drafts, tracks, predicts and recommends; humans and the field execute and approve.

## 1.6 Core architecture

DMA has four components that operate on every project, running one universal per-stage loop.

The per-stage loop: Create/resume project → DRS Project Manager loads Knowledge Base + Project Memory → Run Stage (Claude executes the workflows) → Collect outputs & update Project Memory → AI Auditor produces report + scores → Approval Gate (human decision) → IF approved unlock next stage & transfer outputs / IF revise re-run named workflow / IF reject branch per gate logic → repeat to the final stage → write Geography Blueprint to Knowledge Base → close project.

### DRS Project Manager (DPM) — the orchestrator

The DPM is the central coordinator of the whole lifecycle. It never produces marketing deliverables — it orchestrates while Claude performs the work.

- Project initialization — on Create Project, build the workspace and metadata.

- Stage management — validate entry conditions, create folders, load KB + memory, track progress/files/risks, collect outputs.

- Context / Project Memory — thread all prior-stage outputs forward; nothing is re-derived.

- Workflow orchestration — run each stage’s sub-workflows in order; respect dependencies.

- Auditor coordination — lock stage, send outputs to the Auditor, attach the report, present Claude’s recommendation and the audit findings together, await the human decision.

- Approval management — render the gate, capture the decision, execute the branch.

- Timeline, Risk Register, governance hooks, project completion.

### AI Auditor (DRS-tuned)

After Claude finishes a stage and before the human gate, the AI Auditor independently validates the outputs. For DRS it is stricter than a generic auditor: it enforces the cardinal rule (below). It checks completeness, evidence quality (within Claims Guardrails), knowledge correctness, alignment to the thesis/objectives/North Star, localization, and missing information; and it runs the cardinal-rule check on any stage that touches public communication or launch. It produces an Audit Report, Confidence Score (0–100), Blocker list, and Missing-Information Report. It recommends; it cannot approve — but a cardinal-rule BLOCKER MUST dominate the gate so a human cannot approve it casually.

### Project Memory

A persistent, structured store the DPM maintains across all stages (schema in Appendix A). It threads: project metadata → geography intelligence → market intelligence (+ scores) → stakeholder map → resistance register → narrative & FAQ → GTM → acquisition → consumer/behaviour data → comms & BTL → infra/ops readiness (ingested) → analytics → metrics → knowledge/lessons.

### Knowledge Base

Read at the start of every project, written to at the end. Contents in Appendix B: DMS architecture, workflow library, RACI, KPI tree, cadence; geography instantiation template and all prior Geography Blueprints; narrative houses, FAQ kits, proof-point banks, claims guardrails; government document templates, SOP library, playbooks, campaign assets; behaviour-barrier libraries; resistance-mitigation patterns; prior performance reports and lessons learned.

## 1.7 The cardinal rule (a hard guardrail)

Communication readiness MUST NEVER exceed operational readiness. The agent MUST refuse to scale public communication ahead of operational reality. This rule is enforced by the AI Auditor at Gate 4 (Awareness Scale-Up) and Gate 5 (Launch Go/No-Go).

## 1.8 Human / AI split model

Each stage carries a split tag:

- AI-LED — Claude does ~90%; a human approves at the gate (e.g. Market Intelligence, narrative drafting).

- CO-PILOT — Claude prepares; a human performs the real-world action (government meeting, workshop, field activation) and feeds results back (e.g. Stakeholder Alignment, Acquisition).

- HUMAN-LED / BOT-TRACKED — humans/field own it; the agent tracks, analyzes and recommends (e.g. Infrastructure, Operations, approvals).

## 1.9 Global rules & guardrails

- Cardinal rule — communication readiness MUST never exceed operational readiness.

- Gate discipline — no stage advances without passing its gate; the DPM enforces this.

- Claims guardrails — the agent MUST NOT generate public claims it cannot evidence.

- Localization gate — public-facing assets MUST cover the geography’s mandatory languages before Awareness Scale-Up.

- Human-only actions — government engagement, approvals, signatures and field execution are human-only.

- Loop-backs are normal — a rejected gate routes to a defined corrective workflow, not failure.

- Everything is owned — every output, risk and gate has a RACI owner.

- Memory before re-work — the agent MUST read Project Memory before regenerating anything.

- Audit before gate — no gate is shown to a human without an attached Audit Report.

# 2. Geography instantiation (project creation)

When a user clicks Create DRS Project, the DPM creates a workspace and stores metadata:

| Field | Example value |
| --- | --- |
| Project ID | DRS-GOA-001 (DRS-{GEO}-{seq}) |
| Geography | Goa, India |
| Scope zones | Panaji, Margao, Mapusa, Vasco, airport/beach corridors |
| Implementation model | deposit / PRO model (from config) |
| Languages | English, Konkani, Marathi, Hindi |
| D-Day | target launch date OR “readiness-only” |
| Budget / Objective | optional / public acceptance + return participation |
| Status / Current Stage / Pod Lead | Active / 1 / (e.g. Alokesh) |

Mandatory human inputs at creation: Geography (country + region); implementation model (if known); business objective; D-Day / timeline (or “readiness-only”). Optional: budget, target KPIs, special instructions.

The DPM then loads the DMS Knowledge Base, the geography instantiation template, all prior Geography Blueprints, and the narrative/FAQ banks, and tells Claude: Start Stage 1.

IF a Blueprint already exists for this geography → the DPM MUST pre-fill Stage 1–3 drafts from it and mark each item “validate,” rather than starting blank.

## 2.1 Geography instantiation parameters

Each geography is launched by filling the instantiation template: Country · State/region · Population · Tourism index · Deposit amount · Retailer count · Languages · Machine count · Budget · Government/regulatory context · Priority stakeholders · Public behaviour barriers · Media landscape · Launch timeline · Minimum viable assets.

# 3. The stages

Each stage uses the same skeleton: Objective → Human Input → Claude Input → Claude Workflow → Claude Outputs → AI Auditor → Approval Gate → Data Passed → Success Criteria → Next Stage. The nine DMS workflows are mapped into their stages.

| DMS Workflow | Lives in |
| --- | --- |
| WF1 Research Impact Assessment | Stage 3 Market Intelligence |
| WF2 Stakeholder Mapping | Stage 4 Stakeholder Intelligence |
| WF3 Narrative Development | Stage 6 DRS Marketing System |
| WF4 Stakeholder Alignment | Stage 6 (+ Stage 4 inputs) |
| WF5 Consumer Awareness | Stage 9 Consumer Engagement |
| WF6 Launch Readiness (T-minus) | Stage 6 / Execution |
| WF7 Reputation Management | Stage 10 / post-launch |
| WF8 Collection Optimization | Stage 12 Operations (tracked) |
| WF9 Narrative Amplification | Stage 15 Knowledge Hub |

## Stage 1 — Platform Foundation

Layer: 1 · Project Configuration   Human/AI split: AI-LED   DMS Workflow: —

### Objective

Understand the requirement and create the project foundation.

Entry condition: Project created.

### Human Input

- Geography

- Implementation model

- Business objective

- D-Day / timeline

- Budget (optional), Target KPIs (optional), Special instructions (optional)

### Claude Input (Knowledge Base + Project Memory)

- Project metadata

- Knowledge Base: DMS README, prior Geography Blueprints, SOPs

- Geography instantiation template

### Claude Workflow

WF1.1 — Requirement understanding

- What geography, why now, what outcome is expected

WF1.2 — Historical learning

- Pull similar prior geographies, lessons, best and failed approaches

WF1.3 — Project definition

- Geography/Business Brief, objectives, scope, assumptions, constraints, timeline, success KPIs

WF1.4 — Project foundation

- Executive summary, initial risk register, project metadata, recommended implementation model + module list

### Claude Outputs

- Geography Brief (v0)

- Project Scope

- Objectives & KPIs

- Timeline

- Risk Register (initial)

- Executive Summary

### AI Auditor

Validates:

- Objectives defined; scope complete; KPIs present; timeline realistic

- Correct, latest KB used; similar projects considered

- Missing information; contradictions; business alignment

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate — GATE 0 · Geography Triage

Business Question: Is this geography worth researching? (a cheap, hypothesis-based prioritization — not a launch decision)

Owner: Director Marketing

Claude Recommendation: Explore / Park

Human Actions:

- Approve (Explore)

- Park

- Revise / Add information

Branch logic:

- IF Explore → unlock Stage 2.

- IF Park → status Parked, store the brief, stop (no further cost).

- IF Revise → re-run WF1.3–1.4 with new input.

### Data Passed to Next Stage

- Geography Brief

- Objectives

- Timeline

- KPIs

- Risks

### Success Criteria

- Geography hypothesis defined

- Leadership has chosen to explore or park

### Ifs & Buts (edge cases)

- IF objective is vague → Auditor flags Missing-Info; DPM blocks the gate until clarified.

- IF a Blueprint exists for this geography → pre-fill and mark “validate,” do not start blank.

Next Stage: Stage 2 — Geography Intelligence Engine

## Stage 2 — Geography Intelligence Engine

Layer: 2 · Geography Intelligence   Human/AI split: AI-LED   DMS Workflow: —

### Objective

Build the dynamic administrative + business hierarchy down to outlet level, and the geography’s consumption / tourism / retail profile.

Entry condition: Gate 0 = Explore.

### Human Input

- None (validation only)

### Claude Input (Knowledge Base + Project Memory)

- Geography Brief

- KB geography templates; prior Blueprints

- Public datasets the agent can cite

### Claude Workflow

WF2.1 — Administrative hierarchy (adapts to the geography)

- Goa: District → Taluka → Village Panchayat → Village → Outlet

- Tamil Nadu: District → Corporation → Zone → Ward → Outlet

- United Kingdom: Nation → County → Town → Store

WF2.2 — Business hierarchy & outlet mapping

- Retail landscape, hotels, restaurants, institutions, commercial clusters → outlet universe

WF2.3 — Demand context

- Population, consumption estimates, tourism index, seasonality

WF2.4 — Localization scope

- Set mandatory languages (hard-gate input for later public-facing stages)

WF2.5 — Rollout intelligence

- Priority talukas/zones, high-consumption areas, tourism hotspots, recommended rollout sequence

### Claude Outputs

- Geography Hierarchy

- Outlet Universe

- Consumption / Tourism profile

- Language requirements

- Recommended rollout sequence

### AI Auditor

Validates:

- Hierarchy matches the real geography; outlet universe plausible

- Data sources cited; languages set; coverage gaps flagged

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate

Business Question: Is the geography intelligence complete and correct?

Claude Recommendation: Approve / Revise

Human Actions:

- Approve

- Revise

Branch logic:

- IF Revise → re-run the named WF2.x.

### Data Passed to Next Stage

- Hierarchy

- Outlet universe

- Demand profile

- Languages

- Rollout sequence

### Success Criteria

- Geography fully mapped to outlet level

- Languages locked

### Ifs & Buts (edge cases)

- IF reliable data is unavailable → mark “To be validated by [owner]” rather than fabricating; Auditor flags Missing-Info (not a blocker yet).

- IF tourism index is high → tag the geography “tourism-sensitive” (affects narrative + rollout).

Next Stage: Stage 3 — Market Intelligence

## Stage 3 — Market Intelligence  (DMS begins · WF1)

Layer: 3 · Implementation Intelligence   Human/AI split: AI-LED   DMS Workflow: WF1 Research Impact Assessment

### Objective

Build the evidence base and the decision scores that determine whether to commit to launch.

Entry condition: Stage 2 approved.

### Human Input

- None (validation only)

### Claude Input (Knowledge Base + Project Memory)

- Geography Brief + intelligence

- KB benchmarks, prior research, proof-point bank

### Claude Workflow

WF3.1 — Evidence

- Environmental impact, economic impact, waste ecosystem, litter/leakage context, tourism / public-space relevance

WF3.2 — Policy & benchmarks

- Regulatory context, international DRS case studies, competitor study

WF3.3 — Consumer behaviour & barriers

- Behaviour-barrier hypotheses (barrier → evidence → audience → message → owner)

WF3.4 — ESG & opportunity

- ESG alignment, opportunity assessment, business case, proof-point bank, claims guardrails

WF3.5 — Scoring

- Compute Market Readiness Score, Implementation Complexity, Opportunity Score

### Claude Outputs

- Research Impact Brief

- Business Case

- Proof-Point Bank

- Claims Guardrails

- Behaviour-barrier hypotheses

- The three decision scores

### AI Auditor

Validates:

- Evidence sourced; benchmarks relevant; claims within guardrails

- Scores justified by data; missing evidence flagged

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate — GATE 1 · Geography Selection (the real commit)

Business Question: Is this geography worth launching / committing to?

Owner: Director Marketing + Leadership

Claude Recommendation: Select / Defer

Human Actions:

- Approve (Select)

- Defer

- Revise

Branch logic:

- IF Select → unlock Stage 4; the project enters expensive execution.

- IF Defer → status Deferred, store evidence, stop.

- IF Opportunity Score < threshold OR regulatory blocked → the agent MUST recommend Defer.

### Data Passed to Next Stage

- Research brief, business case

- Proof points, claims guardrails

- Behaviour barriers

- The three scores

### Success Criteria

- Leadership has a defensible Select/Defer decision backed by scores

### Ifs & Buts (edge cases)

- IF scores conflict (high opportunity, high complexity) → the Auditor surfaces the trade-off explicitly; the gate stays a human judgement.

- IF evidence cannot answer a likely stakeholder objection → flag as a research gap to close before Stage 6.

Next Stage: Stage 4 — Stakeholder Intelligence (only on Select)

## Stage 4 — Stakeholder Intelligence  (WF2)

Layer: 3 · Implementation Intelligence   Human/AI split: CO-PILOT   DMS Workflow: WF2 Stakeholder Mapping

### Objective

Identify everyone who can accelerate or block adoption, and score them.

Entry condition: Gate 1 = Select.

### Human Input

- Known contacts, prior relationships, field knowledge (fed in as available)

### Claude Input (Knowledge Base + Project Memory)

- Geography intelligence; regulatory context

- KB stakeholder patterns; prior Blueprints

### Claude Workflow

WF4.1 — Government track

- Departments, officials, pollution board, municipal authorities, tourism department

WF4.2 — Ecosystem track

- PIBO/brands, retail, hotels, restaurants, municipality, panchayat, collectors, NGOs, media, universities, influencers

WF4.3 — Scoring

- For each: influence × current stance × desired role × priority (P0–P2)

WF4.4 — Outputs

- Influence Matrix, Champion List, Blocker/Risk List, Engagement Priority Plan

WF4.5 — Per-stakeholder record

- Support · Influence · Interest · Resistance · Engagement · Meetings · Follow-ups · Documents · Communication History

### Claude Outputs

- Stakeholder Map

- Influence Matrix

- Champion List

- Blocker List

- Engagement Plan

### AI Auditor

Validates:

- All categories covered; P0 stakeholders identified

- Champions & blockers named; single-threading risk; missing roles

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate

Business Question: Have all launch-critical stakeholders been identified and prioritized?

Claude Recommendation: Approve / Revise / Request more

Human Actions:

- Approve

- Revise

- Request additional analysis

### Data Passed to Next Stage

- Stakeholder map + matrices (to Stage 5 and Stage 6)

### Success Criteria

- Complete, scored stakeholder universe with champions and blockers

### Ifs & Buts (edge cases)

- IF a P0 government stakeholder is “Unknown” stance → flag as top risk; the agent drafts a first-meeting brief but the meeting is human-led.

- IF a blocker has high influence → auto-create a Resistance item (Stage 5) and a mitigation owner.

Next Stage: Stage 5 — Resistance Intelligence

## Stage 5 — Resistance Intelligence

Layer: 3 · Implementation Intelligence   Human/AI split: AI-LED + CO-PILOT   DMS Workflow: —

### Objective

Consolidate everything that could block adoption and plan mitigation. DRS-specific; no Marketplace/EPR equivalent.

Entry condition: Stage 4 approved.

### Human Input

- Field signals, political context

### Claude Input (Knowledge Base + Project Memory)

- Stakeholder blockers/concerns; behaviour barriers; media signals

- KB resistance-mitigation patterns

### Claude Workflow

WF5.1 — Fronts

- Government, Retail, Consumer, Brand, Media, Political, Operational

WF5.2 — Per item

- Root Cause → Impact → Probability → Severity → Mitigation → Owner → Status → Review Date

WF5.3 — Signals

- Compute Resistance Index, Sentiment Map, Heat Map, Trend

WF5.4 — Prediction

- Predict likely future resistance and recommend pre-emptive mitigation

### Claude Outputs

- Resistance Register

- Resistance Index

- Sentiment Map

- Heat Map

- Mitigation plan with owners

### AI Auditor

Validates:

- Each front assessed; high-severity items have owners + mitigation; index justified

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate — GATE 2 · Stakeholder Readiness

Business Question: Are launch-critical stakeholders aligned enough to proceed?

Claude Recommendation: Proceed / Engage more

Human Actions:

- Proceed

- Engage more

Branch logic:

- IF Proceed → unlock Stage 6.

- IF Engage more → loop back to Stage 4 alignment activities; re-gate after.

- IF a high-severity blocker is unmitigated → the agent MUST recommend Engage more.

### Data Passed to Next Stage

- Resistance Register + index (to Stage 6 and Reputation in Stage 10)

### Success Criteria

- Known resistance is mapped, owned, and mitigated or accepted

### Ifs & Buts (edge cases)

- IF the Resistance Index rises above threshold at any later stage → the DPM re-opens this stage (loop-back) before proceeding.

Next Stage: Stage 6 — DRS Marketing System

## Stage 6 — DRS Marketing System (Core)  (WF3 + WF4 + WF6)

Layer: 3 · Implementation Intelligence   Human/AI split: AI-LED + CO-PILOT   DMS Workflow: WF3 Narrative · WF4 Alignment · WF6 Launch Readiness

### Objective

Turn evidence + stakeholders into a repeatable narrative, align stakeholders, and run launch readiness. This is the DMS core.

Entry condition: Gate 2 = Proceed.

### Human Input

- Stakeholder feedback from workshops

- Government alignment outcomes

### Claude Input (Knowledge Base + Project Memory)

- Research brief, proof points, claims guardrails

- Stakeholder map, behaviour barriers, languages

### Claude Workflow

WF6a — Narrative Development (DMS WF3)

- Narrative House → Persona Messaging Matrix → FAQ Kit → whitepapers/op-eds/roundtable briefs → localized message bank (mandatory languages)

WF6b — Stakeholder Alignment (DMS WF4)

- Workshop agendas, briefing kits, demonstration plans, Commitment Tracker, updated Concern Log (workshops are human-led; the agent prepares and captures)

WF6c — Launch Readiness (DMS WF6 — the T-minus engine)

- Build T-90 / T-60 / T-30 / T-15 / Launch / T+14 plan; each milestone has owner, status, and a go/no-go confidence score

- Ingests Infrastructure (Stage 11) and Operations (Stage 12) readiness

### Claude Outputs

- Narrative House

- FAQ Kit

- Persona Matrix

- Localized Message Bank

- Commitment Tracker

- T-minus Launch Plan

### AI Auditor

Validates:

- Narrative evidence-backed & within claims guardrails; persona coverage; FAQ completeness

- Localization complete

- Cardinal-rule check: comms readiness vs ops readiness on the T-minus plan

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate — GATE 3 · Narrative Approval

Business Question: Is the story clear, consistent, and evidence-backed?

Owner: Director Marketing

Claude Recommendation: Approve / Revise

Human Actions:

- Approve

- Revise

Branch logic:

- IF Approve → unlock Stage 7.

- IF Revise → re-run WF6a with stakeholder input.

### Data Passed to Next Stage

- Narrative + FAQ + message bank + T-minus plan (to Stages 7–10)

### Success Criteria

- One approved narrative every stakeholder can repeat

- Launch plan exists

### Ifs & Buts (edge cases)

- IF stakeholders interpret DRS inconsistently in workshops → loop WF6a (narrative revision) before proceeding.

- IF localization incomplete → Auditor BLOCKER; cannot pass into public-facing stages.

Next Stage: Stage 7 — Go-To-Market Engine

## Stage 7 — Go-To-Market Engine

Layer: 3 · Implementation Intelligence   Human/AI split: AI-LED   DMS Workflow: —

### Objective

Convert the approved narrative into a complete go-to-market plan.

Entry condition: Gate 3 = Approve.

### Human Input

- Budget constraints, channel preferences

### Claude Input (Knowledge Base + Project Memory)

- Narrative, personas, message bank

- Geography rollout sequence, budget

### Claude Workflow

WF7.1 — GTM build

- Segmentation → Target Personas → Positioning → Messaging → Channels → Campaign Calendar → Budget allocation → Execution plan → Monitoring → Optimization

### Claude Outputs

- GTM Blueprint

- Campaign Framework

- Channel Plan

- Campaign Calendar

- Budget plan

- KPI plan

### AI Auditor

Validates:

- GTM complete; channels matched to behaviour barriers; budget aligned; KPI coverage

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate

Business Question: Is the GTM strategy approved?

Claude Recommendation: Approve / Revise

Human Actions:

- Approve

- Revise

### Data Passed to Next Stage

- GTM blueprint (to Stages 8–10)

### Success Criteria

- Complete, costed GTM aligned to the rollout sequence

### Ifs & Buts (edge cases)

- IF budget insufficient for full rollout → the agent proposes a phased rollout matched to priority zones.

Next Stage: Stage 8 — Acquisition Engine

## Stage 8 — Acquisition Engine

Layer: 3 · Implementation Intelligence   Human/AI split: CO-PILOT   DMS Workflow: —

### Objective

Build and prioritize the partner universe and pipeline.

Entry condition: Stage 7 approved.

### Human Input

- Meeting outcomes, proposals, negotiations (real-world)

### Claude Input (Knowledge Base + Project Memory)

- Stakeholder map, GTM, geography outlet universe

### Claude Workflow

WF8.1 — Universe

- Government · PIBO · Brands · Retail · Hotels · Restaurants · Bars · Beach Shacks · Casinos · Schools · Colleges · Municipality · Panchayat · CSR · NGOs · Collectors · Recyclers

WF8.2 — Pipeline

- Universe → Priority → Target → Contact → Meeting → Proposal → Negotiation → Approval → Agreement → Onboarding → Activation

WF8.3 — Intelligence

- Lead score, priority, suggested follow-up, meeting-summary drafting

### Claude Outputs

- Target universe

- Prioritized pipeline

- Lead scores

- Follow-up plans

- Meeting-summary drafts

### AI Auditor

Validates:

- Universe coverage; prioritization logic; pipeline hygiene; retail readiness inputs for Gate 4

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate — GATE 4 · Awareness Scale-Up

Business Question: Can public communication begin?

Owner: DMS Pod Lead

Claude Recommendation: Scale / Hold

Human Actions:

- Scale

- Hold

Branch logic:

- IF retail readiness < threshold OR operational readiness absent OR localization incomplete → MUST Hold (Auditor BLOCKER, cardinal rule).

- IF Scale → unlock Stage 9 (public awareness).

### Data Passed to Next Stage

- Pipeline + activation data (to Stages 9–10)

### Success Criteria

- Partner pipeline live; readiness confirmed before public comms

### Ifs & Buts (edge cases)

- IF P0 retail partners are not onboarded → Hold; do not scale awareness in those zones.

Next Stage: Stage 9 — Consumer Engagement

## Stage 9 — Consumer Engagement  (WF5)

Layer: 4 · Execution Intelligence   Human/AI split: AI-LED + CO-PILOT   DMS Workflow: WF5 Consumer Awareness

### Objective

Build public understanding and participation intent; drive behaviour change.

Entry condition: Gate 4 = Scale.

### Human Input

- Field activation results, consumer feedback

### Claude Input (Knowledge Base + Project Memory)

- Narrative, message bank, behaviour barriers, channels, languages

### Claude Workflow

WF9.1 — Engagement journey

- Awareness → Education → School → College → Community → Retail → Airport → Tourism → Digital → CSR → Feedback → Sentiment → Behaviour Change

WF9.2 — Behaviour-barrier activation

- For each barrier: deploy the matched message at the right return-moment channel; assign owner; measure comprehension

WF9.3 — Asset production

- Awareness creatives, explainers, school kits, retail signage, social/influencer briefs (localized)

### Claude Outputs

- Consumer Awareness Plan

- Localized assets

- Channel calendar

- Behaviour-barrier tracker

- Sentiment baseline

### AI Auditor

Validates:

- Assets localized; messages matched to barriers; comprehension-test plan present; claims within guardrails

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate

Business Question: Is the consumer awareness program approved to run?

Claude Recommendation: Approve / Revise

Human Actions:

- Approve

- Revise

### Data Passed to Next Stage

- Awareness data + sentiment (to Stage 10 and Analytics)

### Success Criteria

- Awareness live; behaviour barriers actively addressed and measured

### Ifs & Buts (edge cases)

- IF consumers don’t understand deposit/return/reward mechanics (low comprehension) → loop to revise messaging.

- IF return points are not yet live → publish education only, not location/process guidance (cardinal rule).

Next Stage: Stage 10 — Communication & BTL

## Stage 10 — Communication & BTL  (+ WF7 Reputation)

Layer: 4 · Execution Intelligence   Human/AI split: AI-LED + CO-PILOT   DMS Workflow: WF7 Reputation Management

### Objective

Run audience-specific communication, execute BTL, and protect reputation through launch.

Entry condition: Stage 9 approved.

### Human Input

- BTL vendor execution, event delivery, spokesperson actions

### Claude Input (Knowledge Base + Project Memory)

- Narrative, stakeholder map, resistance register, media landscape

### Claude Workflow

WF10.1 — Communication

- Internal · Government · Retail · Consumer · Media · Brand · Partner comms plans + assets

WF10.2 — BTL

- Planning → Calendar → Vendor brief → Material → Execution plan → Attendance → Bottle-collection capture → ROI → Reports

WF10.3 — Reputation (DMS WF7)

- Media monitoring, social listening, misinformation detection, Rapid Response Brief (with SLA), retail testimonials, milestone comms

### Claude Outputs

- Communication plans

- BTL plan + ROI tracker

- Rapid Response protocol

- Media monitoring + sentiment reports

### AI Auditor

Validates:

- Audience coverage; BTL ROI tracking; rapid-response SLA defined; escalation paths set

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate — GATE 5 · Launch Go / No-Go

Business Question: Is the public promise operationally ready to launch?

Owner: DMS Pod Lead + Operations

Claude Recommendation: Go / Go-with-conditions / Delay

Human Actions:

- Go

- Go with conditions

- Delay

Branch logic:

- IF machine readiness < threshold at T-15 OR retail readiness < threshold → No-Go or Conditional (limited zones).

- IF Go → proceed to launch + post-launch.

- IF Delay → reset T-minus, loop readiness items.

### Data Passed to Next Stage

- Launch package + reputation feeds (to Analytics and Operations)

### Success Criteria

- Synchronized launch where the public promise matches operational reality

### Ifs & Buts (edge cases)

- IF negative sentiment spikes pre-launch → trigger Rapid Response within SLA; escalate to Communications Head; may force Delay.

Next Stage: Stages 11/12 (tracked) → Stage 13

## Stage 11 — Infrastructure  (TRACKED DEPENDENCY)

Layer: 4 · Execution Intelligence   Human/AI split: HUMAN-LED / BOT-TRACKED   DMS Workflow: —

### Objective

Stand up machines/return points. The agent does not execute this — it ingests readiness.

Entry condition: In parallel with Stages 9–10.

### Human Input

- Readiness status per site (from ops/field)

### Claude Input (Knowledge Base + Project Memory)

- Site/installation status feeds

### Claude Workflow

WF11.1 — Bot role (track, don’t execute)

- Track Site Identification → Survey → Power → Internet → Permission → Installation → Commissioning → Maintenance → Machine Analytics

- Surface readiness % into Gates 4 and 5; raise risks; recommend sequencing aligned to priority zones

### Claude Outputs

- Infrastructure readiness dashboard (ingested)

- Launch-risk flags

### AI Auditor

Validates:

- Feeds the cardinal-rule check (comms vs ops readiness)

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate

Business Question: (No standalone gate — feeds Gate 5 Launch Go/No-Go)

Claude Recommendation: —

Human Actions:

- —

### Data Passed to Next Stage

- Readiness % (to Stage 6 T-minus plan and Gate 5)

### Success Criteria

- Accurate, current site readiness available to the launch decision

### Ifs & Buts (edge cases)

- IF readiness lags the T-minus plan → the agent raises a launch risk and recommends Conditional Launch or Delay.

Next Stage: Stage 12 — Operations

## Stage 12 — Operations  (TRACKED DEPENDENCY · WF8 Collection Optimization)

Layer: 4 · Execution Intelligence   Human/AI split: HUMAN-LED / BOT-TRACKED   DMS Workflow: WF8 Collection Optimization

### Objective

Run the return-to-recycler loop. The agent tracks and optimizes; it does not run logistics.

Entry condition: Post-launch.

### Human Input

- Operational execution (collection, sorting, transport, recycling)

### Claude Input (Knowledge Base + Project Memory)

- Return/collection/cost data feeds; consumer & retailer feedback

### Claude Workflow

WF12.1 — Ingest

- Bottle Return → Validation → Refund → Collection → Sorting → Transport → Recycler → PCR → Brand → Reporting

WF12.2 — Collection Optimization (DMS WF8)

- Diagnose location friction, behaviour gaps, cost per container, repeat participation; recommend nudges and comms updates

### Claude Outputs

- Collection dashboard

- Location performance report

- Friction log

- Optimization recommendations

- Updated awareness messages

### AI Auditor

Validates:

- Data quality; KPI accuracy; recommendation quality

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate — GATE 6 · Post-Launch Optimization

Business Question: What must improve first?

Owner: Operations + Marketing

Claude Recommendation: Pick the workflow to fix

Human Actions:

- Continue

- Investigate

- Optimize (pick workflow)

Branch logic:

- Route the chosen fix back to the relevant stage (awareness / retail / location / messaging) as a loop-back.

### Data Passed to Next Stage

- Optimization insights (to Stage 9 awareness, Stage 10 comms)

### Success Criteria

- Return rate and cost improving; friction reduced

### Ifs & Buts (edge cases)

- IF return rate < target OR cost per container rises → auto-open an optimization loop and feed insights to Stages 9 and 10.

Next Stage: Stage 13 — Analytics

## Stage 13 — Analytics

Layer: 5 · Performance Intelligence   Human/AI split: AI-LED   DMS Workflow: —

### Objective

Provide role-based dashboards, all filtering by geography + implementation model, all rolling up to the Adoption Index.

Entry condition: Launch onward.

### Human Input

- None (review only)

### Claude Input (Knowledge Base + Project Memory)

- All performance, awareness, stakeholder, ops and finance data feeds

### Claude Workflow

WF13.1 — Dashboards

- Generate/refresh Executive · Project · Marketing · Stakeholder · Government · Acquisition · BTL · Infrastructure · Operations · Finance · Knowledge dashboards

WF13.2 — Reporting

- Daily / weekly / monthly reports; Adoption Index trend

### Claude Outputs

- Dashboards

- Daily/weekly/monthly reports

- Adoption Index trend

### AI Auditor

Validates:

- Data quality, KPI accuracy, dashboard consistency, decision-support readiness

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate

Business Question: Is performance meeting objectives?

Claude Recommendation: Continue / Investigate / Optimize

Human Actions:

- Continue

- Investigate

- Move to Optimization

### Data Passed to Next Stage

- Performance insights (to Stage 12 loop and governance reviews)

### Success Criteria

- Performance fully measured; objectives validated; optimization opportunities identified

### Ifs & Buts (edge cases)

- IF the Adoption Index declines for 2 cycles → the DPM raises a system-health alert for the monthly review.

Next Stage: Stage 14 — Metrics Engine

## Stage 14 — Metrics Engine

Layer: 5 · Performance Intelligence   Human/AI split: AI-LED   DMS Workflow: —

### Objective

Expose every module’s metrics with full transparency; separate leading from lagging indicators.

Entry condition: Continuous.

### Human Input

- None

### Claude Input (Knowledge Base + Project Memory)

- Every module’s KPI definitions and data sources

### Claude Workflow

WF14.1 — Metrics contract

- Each module exposes: Objective · KRA · KPI · Formula · Data Source · Frequency · Target · Actual · Variance · Trend · Owner

WF14.2 — Leading vs lagging

- Leading: stakeholders mapped/briefed, champion commitments, concerns resolved, message comprehension, retail readiness, launch-readiness score

- Lagging: containers returned, return rate, active users, repeat returns, retail participation, cost per container, sentiment trend

### Claude Outputs

- Metrics tree mapped to the North Star

### AI Auditor

Validates:

- Formula correctness; data-source validity; North-Star alignment

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate

Business Question: (No gate — continuous metrics layer)

Claude Recommendation: —

Human Actions:

- —

### Data Passed to Next Stage

- Metrics tree (to Analytics and governance)

### Success Criteria

- Transparent, owned metrics rolling up to the Adoption Index

### Ifs & Buts (edge cases)

- IF a KPI lacks a data source → the Auditor flags it as Missing-Info.

Next Stage: Stage 15 — Knowledge Hub

## Stage 15 — Knowledge Hub  (WF9 Narrative Amplification + cloning)

Layer: 5 · Performance Intelligence   Human/AI split: AI-LED   DMS Workflow: WF9 Narrative Amplification

### Objective

Capture everything reusable and produce the next-geography blueprint.

Entry condition: Milestones achieved.

### Human Input

- Manual notes, leadership observations, special learnings (optional)

### Claude Input (Knowledge Base + Project Memory)

- The complete project history

### Claude Workflow

WF15.1 — Narrative Amplification (DMS WF9)

- Turn milestones into case studies, PR, social proof; equip stakeholders with proof

WF15.2 — Knowledge capture

- SOP library, playbooks, templates, government documents, campaign assets, research papers, lessons learned, best practices

WF15.3 — Reusable Geography Blueprint

- Package evidence, narrative, FAQ, stakeholder patterns, and playbook so the next geography starts ahead

### Claude Outputs

- Updated Knowledge Base

- Geography Blueprint

- Lessons-learned report

- Executive closure report

### AI Auditor

Validates:

- Correct categorization; version control; duplicate detection; reusability

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate — GATE 7 · Amplification

Business Question: Is there credible proof to share?

Owner: Marketing + Communications

Claude Recommendation: Amplify / Wait

Human Actions:

- Amplify

- Wait

Branch logic:

- IF no credible milestone yet → Wait; capture internally, do not publish externally.

### Data Passed to Next Stage

- Geography Blueprint (to the Knowledge Base, for the next geography)

### Success Criteria

- Knowledge Base updated; Blueprint generated; project officially completed

### Ifs & Buts (edge cases)

- IF a milestone is achieved but not communicated → the agent prompts amplification at the weekly review.

Next Stage: Project close (or loop to the next geography)

## Stage 16 — AI Copilot  (CROSS-CUTTING)

Layer: Cross-cutting   Human/AI split: AI-LED (assist only)   DMS Workflow: —

### Objective

Embed AI assistance throughout every stage — not a standalone chatbot.

Entry condition: All stages.

### Human Input

- Questions / requests in context

### Claude Input (Knowledge Base + Project Memory)

- Project Memory + Knowledge Base

### Claude Workflow

WF16.1 — Capabilities

- Research summarization, case-study retrieval, stakeholder insights, meeting summaries, GTM drafting, campaign/FAQ/PR generation, KPI explanations, trend analysis, resistance recommendations, report/presentation generation, knowledge search

### Claude Outputs

- In-context assistance across every stage

### AI Auditor

Validates:

- Outputs respect claims guardrails and the cardinal rule

Produces: Audit Report · Confidence Score · Blocker List · Missing-Information Report

### Approval Gate

Business Question: (Cross-cutting — no gate)

Claude Recommendation: —

Human Actions:

- —

### Data Passed to Next Stage

- Accelerated outputs into each stage

### Success Criteria

- AI advises and accelerates; approvals and execution stay with humans

### Ifs & Buts (edge cases)

- Principle — AI advises and accelerates; approvals and execution stay with the marketing and implementation teams.

Next Stage: —

# 4. The DMS engine in full — the nine workflows

The agent’s stages are powered by the DMS’s nine workflows. Each is specified here with its purpose, inputs, activities, outputs, KPIs, RACI, AI agents, templates, review frequency, and optimization triggers, so nothing from the Director’s DMS is lost.

## WF1 — Research Impact Assessment

Primary owner: Marketing    Primary outcome: Evidence base for DRS adoption

Purpose: Understand the environmental, economic and social case for DRS in the target geography.

Inputs: Geography context · waste/litter data · tourism/public-space data · consumption estimates · international DRS benchmarks · regulatory context · past pilot/collection data.

Activities: Study comparable DRS systems; estimate local environmental & tourism impact; build the economic & social case; identify behaviour barriers; convert evidence into proof points.

Outputs: Research impact brief · case studies · business case · behaviour-insight notes · proof-point bank.

KPIs: Research brief completed · validated proof points · stakeholder questions answered by evidence · evidence gaps · narrative inputs on time.

RACI: R: Marketing · A: Marketing Head · C: Operations, Government Affairs, ESG, Data · I: Director Marketing, Pod Lead.

AI agents: Research synthesis agent · benchmarking agent · evidence-to-message agent.

Templates: Research impact brief · case study · proof-point bank.

Review frequency: Weekly before narrative approval; monthly after launch.

Optimization triggers: Stakeholders ask questions evidence cannot answer; public objections on impact/credibility; collection data contradicts assumptions.

## WF2 — Stakeholder Mapping

Primary owner: Government Affairs    Primary outcome: Influence map and champion list

Purpose: Identify stakeholders who can accelerate, enable, influence or block adoption.

Inputs: Geography brief · regulatory context · retailer/brand landscape · municipality/pollution-board context · media/influencer landscape · NGO/school/academic ecosystem.

Activities: Map government & regulatory stakeholders, retailers, brands, municipalities, NGOs, journalists, academics, influencers; score influence & stance; identify champions & blockers; set engagement priority.

Outputs: Stakeholder map · influence matrix · champion list · blocker/risk list · engagement priority plan.

KPIs: Map completion · priority stakeholders identified · champion completeness · stakeholders engaged · readiness score.

RACI: R: Government Affairs · A: Gov Affairs Head · C: Marketing, Partnerships, Operations · I: Director Marketing, Pod Lead.

AI agents: Stakeholder mapping assistant · influence scoring assistant · briefing-note agent.

Templates: Stakeholder map · influence matrix · champion list.

Review frequency: Weekly before launch; monthly after.

Optimization triggers: A priority stakeholder is unengaged; a blocker gains influence; coalition gaps delay launch.

## WF3 — Narrative Development

Primary owner: Marketing    Primary outcome: Geography-specific DRS narrative

Purpose: Create the core DRS story and stakeholder-specific messages for the geography.

Inputs: Research brief · proof-point bank · stakeholder map · behaviour barriers · local-language needs · sentiment signals.

Activities: Build narrative house; draft persona messaging; create FAQ kit; develop whitepapers/op-eds/roundtable themes; validate with priority stakeholders; translate & localize.

Outputs: Narrative house · persona messaging matrix · FAQ kit · whitepaper/op-ed · roundtable brief · localized message bank.

KPIs: Narrative approved · priority-stakeholder message fit · FAQ completeness · content assets completed · message recall/comprehension.

RACI: R: Marketing · A: Marketing Head · C: Gov Affairs, Communications, Operations, Legal/Policy · I: Director Marketing, Pod Lead.

AI agents: Narrative strategist · persona messaging agent · FAQ generator · localization assistant.

Templates: Narrative house · persona messaging matrix · FAQ kit.

Review frequency: Weekly before launch; monthly after.

Optimization triggers: Stakeholders interpret DRS inconsistently; consumer questions reveal confusion; media frames DRS incorrectly.

## WF4 — Stakeholder Alignment

Primary owner: Government Affairs    Primary outcome: Coalition support & readiness

Purpose: Prepare influential stakeholders to support, explain and participate in the launch.

Inputs: Stakeholder map · champion list · narrative house · FAQ kit · demonstration plan · pilot/site-visit options.

Activities: Conduct workshops; share FAQ kits & briefing notes; host demonstration visits; arrange pilot visits; capture concerns and update assets; secure visible champions and participation commitments.

Outputs: Workshop report · stakeholder briefing kits · demonstration log · commitment tracker · updated concern log.

KPIs: Priority stakeholders briefed · readiness score · champion commitments · open concerns resolved · partner participation commitments.

RACI: R: Government Affairs · A: Gov Affairs Head · C: Marketing, Operations, Partnerships, Communications · I: Director Marketing, Pod Lead.

AI agents: Briefing-kit assistant · concern-summarization agent · commitment-tracker assistant.

Templates: Stakeholder briefing kit · workshop agenda · concern & commitment tracker.

Review frequency: Weekly before launch.

Optimization triggers: Stakeholder readiness stays low; repeated concerns emerge; a launch-critical stakeholder is not aligned.

## WF5 — Consumer Awareness

Primary owner: Marketing    Primary outcome: Public understanding & participation intent

Purpose: Build public understanding and participation intent before and during launch.

Inputs: Narrative house · behaviour barriers · language requirements · launch locations · retail/machine locations · school/airport/transit/social/influencer channels.

Activities: Run school awareness; activate retail awareness; activate airport/transit comms; publish social & influencer content; use local-language explainers; promote how/where/why to return.

Outputs: Consumer awareness plan · channel calendar · retail/store assets · school activation kit · social content · influencer briefs.

KPIs: Awareness reach · message comprehension · retail asset deployment · sessions completed · social engagement · inquiry volume · participation intent.

RACI: R: Marketing · A: Marketing Head · C: Retail/Partner, Operations, Communications, Influencer Partners · I: Director Marketing, Pod Lead.

AI agents: Consumer copy agent · local-language adaptation agent · social content agent · channel-planning assistant.

Templates: Consumer awareness plan · retail asset checklist · school activation kit · influencer brief.

Review frequency: Weekly before and during launch.

Optimization triggers: Awareness reach low; consumers don’t understand deposit/return/reward; retail teams report repeated questions.

## WF6 — Launch Readiness

Primary owner: DMS Pod Lead    Primary outcome: Synchronized comms & operational readiness

Purpose: Synchronize communication, stakeholder, retail, machine-demo and launch-day execution.

Inputs: Launch date · awareness plan · stakeholder readiness · retail onboarding · machine deployment/demo status · media plan · event plan.

Activities: Run T-90 awareness, T-60 retail onboarding, T-30 mass-media, T-15 machine-demo readiness; prepare launch-day plan; conduct go/no-go review.

Outputs: Launch readiness tracker · T-minus plan · go/no-go decision · launch-day runbook · issue log.

KPIs: T-minus milestones completed · retail onboarding readiness · machine/demo readiness · awareness deployment · issue closure · go/no-go confidence.

RACI: R: DMS Pod Lead · A: DMS Pod Lead · C: Marketing, Operations, Retail/Partner, Communications, Gov Affairs · I: Director Marketing, Leadership.

AI agents: Launch-checklist assistant · issue-log summarizer · runbook generator.

Templates: Launch readiness tracker · launch-day runbook · go/no-go checklist.

Review frequency: Weekly T-90 to T-30; twice weekly T-30 to launch.

Optimization triggers: Any T-minus milestone delayed; communication readiness exceeds operational readiness; risks unresolved at T-15.

## WF7 — Reputation Management

Primary owner: Communications    Primary outcome: Trust protection & rapid response

Purpose: Protect trust before and after launch by monitoring narratives, responding quickly, and amplifying credible proof.

Inputs: Media monitoring · social listening · stakeholder concerns · retail feedback · collection milestones · incident reports.

Activities: Monitor sentiment; identify misinformation; prepare rapid responses; capture testimonials; communicate milestones; route operational issues to owners.

Outputs: Media monitoring report · rapid response brief · issue response log · testimonial bank · milestone communication.

KPIs: Response turnaround · negative-issue closure · sentiment trend · misinformation resolved · testimonials collected · milestones communicated.

RACI: R: Communications · A: Communications Head · C: Marketing, Operations, Gov Affairs, Legal/Policy · I: Director Marketing, Pod Lead.

AI agents: Media-monitoring summarizer · rapid-response drafting agent · sentiment classifier.

Templates: Rapid response brief · media monitoring log · testimonial capture.

Review frequency: Daily during launch window; weekly post-launch.

Optimization triggers: Negative sentiment rises; misinformation spreads; operational issues create reputation risk.

## WF8 — Collection Optimization

Primary owner: Operations    Primary outcome: Improved return rate & efficiency

Purpose: Improve return behaviour, retail participation and collection efficiency using operational and behavioural data.

Inputs: Containers returned · return rate · cost per container · active users · retail participation · location performance · consumer & retailer feedback.

Activities: Analyze return patterns; identify low-performing locations & friction; recommend behaviour nudges; update retail/machine comms; feed insights to awareness & reputation.

Outputs: Collection dashboard · location performance report · friction log · optimization recommendations · updated awareness messages.

KPIs: Containers returned · return rate · cost per container · active users · retail participation · repeat returns · location improvement.

RACI: R: Operations · A: Operations Head · C: Marketing, Retail/Partner, Data · I: Director Marketing, Pod Lead.

AI agents: Collection data analyst · friction classifier · optimization recommendation assistant.

Templates: Collection dashboard · friction log · location optimization brief.

Review frequency: Weekly after launch.

Optimization triggers: Return rate below target; cost per container rises; specific locations underperform; consumer friction repeats.

## WF9 — Narrative Amplification

Primary owner: Marketing    Primary outcome: Proof-led adoption story for scale

Purpose: Turn milestones and proof into stronger adoption stories for the current and future geographies.

Inputs: Collection milestones · impact data · stakeholder & retail testimonials · media wins · before/after visuals · community stories.

Activities: Build milestone stories; publish case studies; create PR & social amplification; equip stakeholders with proof; update research & narrative; package learnings for the next geography.

Outputs: Milestone campaign · case study · PR story · social proof assets · updated playbook · next-geography briefing.

KPIs: Milestones amplified · earned media · stakeholder endorsements · case studies completed · next-geography assets updated · positive sentiment movement.

RACI: R: Marketing · A: Marketing Head · C: Communications, Operations, Gov Affairs, Retail/Partner · I: Director Marketing, Leadership.

AI agents: Case-study writer · PR-angle generator · social-proof asset assistant.

Templates: Milestone story · case study · next-geography briefing.

Review frequency: Monthly after launch.

Optimization triggers: Milestones achieved but not communicated; future-geography teams lack proof; stakeholder confidence needs reinforcement.

# 5. Decision gates — master table

| Gate | Fires after | Question | Owner | Outcomes & branches |
| --- | --- | --- | --- | --- |
| 0 · Geography Triage | Stage 1 | Worth researching? | Director Marketing | Explore → Stage 2 · Park → stop/store · Revise → re-run WF1.3 |
| 1 · Geography Selection | Stage 3 | Worth launching/committing? | Director Mktg + Leadership | Select → Stage 4 · Defer → park · auto-Defer IF Opportunity<threshold or regulatory blocked |
| 2 · Stakeholder Readiness | Stage 5 | Stakeholders aligned to proceed? | Gov Affairs + Pod Lead | Proceed → Stage 6 · Engage more → loop Stage 4 |
| 3 · Narrative Approval | Stage 6 | Story clear & evidence-backed? | Director Marketing | Approve → Stage 7 · Revise → loop WF6a |
| 4 · Awareness Scale-Up | Stage 8 | Can public comms begin? | Pod Lead | Scale → Stage 9 · Hold (MUST IF readiness/localization incomplete) |
| 5 · Launch Go/No-Go | Stage 10 | Public promise ops-ready? | Pod Lead + Operations | Go · Conditional (limited zones) · Delay (MUST IF readiness<threshold) |
| 6 · Post-Launch Optimization | Stage 12 | What to improve first? | Operations + Marketing | Pick workflow → loop to Stage 9/10/retail |
| 7 · Amplification | Stage 15 | Credible proof to share? | Marketing + Comms | Amplify → publish · Wait → capture internally |

Universal branch rules: Revise = re-run the named workflow, re-audit, re-gate. Reject/Hold/No-Go = do not advance; route to the corrective stage; notify the RACI owner. A cardinal-rule BLOCKER overrides any “Go/Scale” recommendation until resolved. Every loop-back updates Project Memory and the Risk Register.

# 6. Governance, cadence & RACI

## 6.1 Roles (RACI)

- Director Marketing — owns DMS architecture, system health, capability building.

- DMS Pod Lead — owns geography-level execution and launch readiness.

- Marketing Head — owns evidence, narrative, awareness, amplification.

- Government Affairs Head — owns stakeholder mapping and alignment.

- Communications Head — owns reputation, media monitoring, rapid response.

- Operations Head — owns launch operational readiness and collection optimization.

- Retail/Partner Teams — own retail onboarding, site coordination, partner activation.

- Data Team — supports evidence, collection dashboard, optimization analysis.

- Leadership — approves geography priority and major launch decisions.

## 6.2 Decision points

| Decision point | Owner | Trigger | Output |
| --- | --- | --- | --- |
| Select DRS geography | Director Marketing + Leadership | New geography priority | Geography instantiation brief |
| Approve core narrative | Director Marketing | Research & stakeholder inputs complete | Narrative house |
| Move to stakeholder alignment | Marketing + Gov Affairs | Stakeholder map complete | Alignment plan |
| Move to consumer awareness | DMS Pod Lead | Coalition & operational minimums ready | Awareness plan |
| Approve launch readiness | Pod Lead + Operations | T-30 readiness review | Launch go/no-go decision |
| Trigger rapid response | Communications | Negative media, misinformation, stakeholder concern | Response brief |
| Shift optimization focus | Operations + Marketing | Return rate, cost, or friction issue | Collection optimization plan |
| Amplify success story | Marketing + Communications | Milestone or proof point achieved | Case study or campaign |

## 6.3 Cadence

- Daily (T-7 → T+14): launch-window check-in — issues, sentiment, escalations, rapid-response approvals.

- Weekly: workflow standup — readiness, narrative gaps, biggest friction barrier, next actions; updates the weekly dashboard.

- Biweekly: workflow improvement review — fix the one workflow dragging adoption.

- Monthly: system-health review — Adoption Index trend, architecture changes, geography priority.

- Quarterly: geography performance review + Blueprint refresh.

## 6.4 Feedback loops

- Weekly: stakeholder feedback updates narrative & FAQs; consumer questions update awareness; retail/machine friction updates launch readiness; media sentiment updates rapid-response priorities.

- Monthly: collection data updates optimization; milestones update amplification; reputation signals update stakeholder comms; research gaps update the evidence plan.

- Quarterly: geography performance review; coalition review; public-adoption review; playbook update for the next geography.

## 6.5 Escalation rules

- Narrative disputed/unclear → Director Marketing.

- Any T-minus milestone delayed / readiness out of sync / go-no-go confidence drops → DMS Pod Lead.

- Negative media / misinformation / stakeholder concern goes public → Communications Head.

- Return rate / participation / friction below target → Operations Head.

# 7. Metrics engine

## 7.1 North Star roll-up (KPI tree)

- Public Awareness ← reach · comprehension · retail deployment · sessions · social · inquiry volume

- Stakeholder Alignment ← mapped · briefed · champion commitments · concerns resolved · retail readiness

- Return Participation ← containers returned · return rate · active users · repeat returns · retail participation

- Trust & Friction (÷) ← negative sentiment · misinformation · unresolved concerns · machine friction · cost/container · complaints

## 7.2 System-level KPIs

| KPI | Cadence | Owner |
| --- | --- | --- |
| DRS Adoption Index | Weekly during launch, monthly after | DMS Pod Lead |
| Public Awareness | Weekly | Marketing Head |
| Stakeholder Readiness Score | Weekly before launch | Gov Affairs Head |
| Launch Readiness Score | Weekly / twice-weekly near launch | DMS Pod Lead |
| Return Rate | Weekly after launch | Operations Head |
| Cost per Container | Weekly after launch | Operations Head |
| Sentiment Trend | Weekly during launch | Communications Head |

## 7.3 First weekly dashboard columns

Geography · Launch phase · Days to/since launch · Awareness reach · Message comprehension · Priority stakeholders mapped · Priority stakeholders briefed · Champion commitments · Open concerns · Retail readiness · Machine/demo readiness · T-minus status · Containers returned · Return rate · Active users · Retail participation · Cost per container · Sentiment trend · Top friction point · Owner · Next action.

# 8. Readiness & system health

## 8.1 Minimum viable DMS for a geography

A geography is ready for initial launch when these exist:

- One research impact brief

- One stakeholder map

- One influence matrix

- One champion list

- One narrative house

- One FAQ kit

- One consumer awareness plan

- One launch readiness timeline

- One reputation response protocol

- One collection dashboard

## 8.2 System health indicators

Healthy: stakeholders repeat the narrative without heavy prompting; retailers/partners understand their role; consumer awareness rises before launch; the launch-day promise matches operational reality; media sentiment is monitored & managed; return participation improves after launch; milestones become public proof.

Unhealthy: DRS is seen only as waste management / machine deployment; government, retailers, brands & consumers hear different stories; awareness starts too late; launch marketing overpromises operational readiness; negative narratives spread unanswered; collection data does not feed back into communication.

# 9. Knowledge capture & geography cloning

On project completion the agent MUST:

- Write a Geography Blueprint to the KB (evidence + narrative + FAQ + stakeholder patterns + playbook + lessons).

- Update narrative/FAQ banks, proof-point bank, resistance-mitigation patterns, behaviour-barrier library.

- Produce an executive closure report.

- Tag reusable assets for the next geography.

Cloning rule: when a new geography is created, the DPM seeds Stages 1–3 from the most similar Blueprint and marks every seeded item “validate,” so each launch is faster, cheaper and more credible than the last.

# 10. The DRS Project Manager (lifecycle)

The DRS Project Manager (DPM) manages the complete lifecycle of a DRS marketing project. It is the central coordinator for all stages — maintaining project context, validating stage readiness, tracking progress, coordinating the AI Auditor, and ensuring smooth transitions. It never generates marketing deliverables; it orchestrates while Claude performs the work.

## 10.1 Before Stage 1 — initialization

On Create Project, the DPM creates a workspace, stores the metadata (Section 2), loads the Knowledge Base (DMS KB, geography KB, prior Blueprints, templates, SOP library), and tells Claude: Start Stage 1.

## 10.2 Per-stage responsibilities

- Before: validate required inputs; create project & stage folders; load KB + memory.

- During: track Claude progress, files generated, knowledge used, risks found.

- After: collect outputs; save into the stage folder; update Project Memory; call the AI Auditor; receive the audit report; show the Approval Gate; on approval, set current stage = next and transfer outputs.

## 10.3 Auditor coordination (before every gate)

- Lock the current stage.

- Send all stage outputs to the AI Auditor.

- Wait for the audit report.

- Attach the audit report to the stage.

- Present Claude’s recommendation and the audit findings together.

- Wait for the human decision.

- If approved, unlock the next stage and transfer all approved outputs automatically.

## 10.4 The DPM maintains throughout

- Project Memory — metadata → geography → market → stakeholder → resistance → narrative → GTM → acquisition → consumer → comms → dependencies → analytics → metrics → knowledge.

- Timeline — current day vs D-Day, T-minus milestones, tasks completed/pending, upcoming milestones, risks.

- Progress Tracker — % complete per stage.

- Risk Register — Government · Operational · Reputation · Consumer · Resistance risks, continuously updated.

## 10.5 Complete lifecycle

Create Project → DRS Project Manager → Load Knowledge Base → Run Stage → Collect Outputs → Run AI Auditor → Approval Gate → Update Project Memory → Start Next Stage → (repeat to the final stage) → Update Knowledge Base (write Geography Blueprint) → Close Project (archive + executive closure report).

# Appendix A — Project Memory schema (minimum)

project: { id, geography, zones, implementation_model, languages, d_day, budget, status, current_stage, pod_lead }

geography_intelligence: { hierarchy, outlet_universe, demand_profile, rollout_sequence, languages }

market_intelligence: { research_brief, business_case, proof_points, claims_guardrails, scores{readiness, complexity, opportunity}, behaviour_barriers[] }

stakeholders: { map[], influence_matrix, champions[], blockers[] }

resistance: { register[], index, sentiment_map, heat_map }

narrative: { house, persona_matrix, faq_kit, message_bank{by_language}, commitment_tracker, t_minus_plan }

gtm: { blueprint, channels, calendar, budget }    acquisition: { universe[], pipeline[], lead_scores }

consumer: { awareness_plan, assets{by_language}, barrier_tracker, sentiment }

comms_btl: { plans, btl_roi, rapid_response_protocol, media_monitoring }

dependencies: { infrastructure_readiness{by_site}, operations{return_rate, cost_per_container, ...} }

analytics: { dashboards[], adoption_index_trend }    metrics: { tree, leading[], lagging[] }

knowledge: { blueprint, lessons, assets[] }

risk_register: [ {type, item, severity, owner, status} ]    gate_log: [ {gate, decision, owner, timestamp, audit_ref} ]

# Appendix B — Knowledge Base structure

DMS architecture · workflow library · RACI · KPI tree · cadence · geography instantiation template · Geography Blueprints · narrative/FAQ banks · proof-point bank · claims guardrails · government document templates · SOP library · playbooks · campaign assets · behaviour-barrier library · resistance-mitigation patterns · prior performance reports.

# Appendix C — Stage → DMS workflow → Gate map

| Stage | DMS WF | Gate |
| --- | --- | --- |
| 1 Platform Foundation | — | Gate 0 Triage |
| 2 Geography Engine | — | approve/revise |
| 3 Market Intelligence | WF1 | Gate 1 Selection |
| 4 Stakeholder Intelligence | WF2 | approve/revise |
| 5 Resistance Intelligence | — | Gate 2 Stakeholder Readiness |
| 6 DRS Marketing System | WF3, WF4, WF6 | Gate 3 Narrative Approval |
| 7 Go-To-Market | — | approve/revise |
| 8 Acquisition | — | Gate 4 Awareness Scale-Up |
| 9 Consumer Engagement | WF5 | approve/revise |
| 10 Communication & BTL | WF7 | Gate 5 Launch Go/No-Go |
| 11 Infrastructure | — | tracked (feeds Gate 5) |
| 12 Operations | WF8 | Gate 6 Post-Launch Optimization |
| 13 Analytics | — | continue/investigate/optimize |
| 14 Metrics Engine | — | — |
| 15 Knowledge Hub | WF9 | Gate 7 Amplification |
| 16 AI Copilot | — | cross-cutting |

# Appendix D — Glossary

- DRS — Deposit Return System

- DMS — DRS Marketing System (the engine)

- DMA — DRS Marketing Agent (this bot)

- DPM — DRS Project Manager (orchestrator)

- PIBO — Producer / Importer / Brand-Owner

- PRO — Producer Responsibility Organisation

- BTL — Below-The-Line

- PCR — Post-Consumer Resin

- Adoption Index — the North Star metric

- T-minus — the launch countdown (T-90 → T+14)

- Blueprint — the reusable geography pack

End of BRD — DRS Marketing Agent v1.0. This document specifies the architecture, all stages, all workflows (including the full DMS), all gates and branch logic, governance, metrics, readiness and reusable schemas required to build the DRS Marketing Agent.